## Sheet1
Date | Project | Task | Start | End | Description
16 June | Multivendo | Learn PY B | 16 | 18 | Learn PY Basics
17 June | Multivendo |  | 17 | 18 | learn python basics
18 June | Multivendo | User login | 18 | 19 | logic of login signup creation. and familization with project
19 June | Multivendo | forgot pass | 18 | 21 | setup the logic of forget password
20 June | Multivendo | re built forgot passwo | 21 |  | forget password logics with OTP verification with gmail
21 June | Multivendo | leave |  |  | leave
23 June | Multivendo | reset pass | 23 | 23 | reset password based on router
24 June | Multivendo | leave |  |  | college practical
25 June | Multivendo | leave |  |  | college viva
26 June | Multivendo | Image mod | 26 June | 27 June | Creating a image model to store image in the database
28 June | Multivendo | Product m | 28 June | 29 June | Combining everything in a product model to store it in the db
29 June | Multivendo | Sunday
30 June | Multivendo | adding mo | 30 June | 1 July | Adding many type of filters on the product
2 July | Multivendo | create sell | 2 July | 3 July | More APIs like listing the product, refineing the reset password flow
3 July | Multivendo | Seller perm | 3 July | 3 July | giving seller the permission to add their product with stock
4 July | Multivendo | admin perm | 4 July | 4 July | admin permission in which an admin can remove the seller and the product of the seller
5 July | multivendo | create som | 5 July | 5 July | gave special permission to admin
6 July |  | Sunday
7 July | multivendo | create a ca | 7 July | 8 July | creating a cart routes
9 July | multivendo | create a lo | 9 July | 10 July | creating logout APIs
10 July | multivendo | test all AP | 10 | 11 July | test all APIs for deployments
11 July | multivendo | seting ups | 11 July | 11 July | seting cors for connecting backend to front end
12 July | multivendo | deploy pro | 12 July | 12 July | deploy project on render and waiting for next instructions
2025-07-14 | Multivendo | solve cors issues | 2025-07-14 | 2025-07-14 | solve cors isssues
2025-07-15 | no task | no task |  |  | no task
2025-07-16 | multivendor | no task |  |  | no task
2025-07-17 | multivendor |  |  |  | no task
2025-07-18 | data wrapping task provided by vinay sir |  |  |  | data wrapping
19 juky | leave due to collage works |  |  | 2025-07-19 | leave due to collage works
20 july Sunday |  |  | Sunday |  | Sunday |  | Sunday
2025-07-21 | no task |  | no task |  | no task |  | no task
2025-07-22 | multivendor | meeting for multivendor and get task for projects | 2025-07-22 | 2025-07-25 | getting task for projects
2025-07-23 | multivendor | seller appi |  | 2025-07-25 | craeting seller api
2025-07-24 | multivendor | craeting seller api | 2025-07-24 | 2025-07-25 | craeting and testing seller apis
2025-07-25 | Quizz app | create aa quiz app | 2025-07-25 | 2025-07-26 | creating a quiz app for node js
2025-07-26 | quizz app | completion of quiz app | 2025-07-25 | 2025-07-26 | completed the quiz app
2025-07-27 | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday
2025-07-28 | Quizz App | Review Meeting of Quiz App | 2025-07-28 | 2025-07-28 | Review meeting of Quiz app
2025-07-29 | Quiz App | Fix issue on quiz app | 2025-07-29 | 2025-07-29 | Display the user's name and user's email on score card | complte the quiz app